## FR17
ID | Type | Technique / Ref | Input / Action | Expected Result | Audit | Note | Actual Result | Execution Status | Bug ID | Evidence
FR17-TC-001 | Positive | Positive GET | GET coupons bằng admin token | 2xx; body là JSON array | VALID | Reviewed against test-plans/FR17.md. The Positive GET case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 1)
FR17-TC-002 | Security; Equivalence Partitioning | GET auth missing | GET coupons không token | 4xx; không trả coupon list | VALID | Reviewed against test-plans/FR17.md. The GET auth missing case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 2)
FR17-TC-003 | Security | GET role authorization | GET coupons bằng user token | 4xx; không trả coupon list | VALID | Reviewed against test-plans/FR17.md. The GET role authorization case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL | #4 | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 3); https://github.com/venncoder08/HW06_API_Testing/issues/4
FR17-TC-004 | Security; Equivalence Partitioning | GET malformed JWT | GET coupons bằng malformed token | 4xx; không trả coupon list/stack trace | VALID | Reviewed against test-plans/FR17.md. The GET malformed JWT case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 4)
FR17-TC-005 | Security | GET forged JWT | Sửa role user thành admin trong payload, giữ signature cũ | 4xx; không trả coupon list | VALID | Reviewed against test-plans/FR17.md. The GET forged JWT case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 5)
FR17-TC-006 | Security | GET wrong scheme | GET coupons bằng Basic scheme | 4xx; không trả coupon list | VALID | Reviewed against test-plans/FR17.md. The GET wrong scheme case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 6)
FR17-TC-007 | Schema | GET required fields | GET seed coupons bằng admin | Mỗi coupon có code,type,discount_value,min_order_amount,expired_at,max_uses_per_user | VALID | Reviewed against test-plans/FR17.md. The GET required fields case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 7)
FR17-TC-008 | Schema; Equivalence Partitioning | GET type enum | GET seed coupons | Mọi type là percent hoặc fixed | VALID | Reviewed against test-plans/FR17.md. The GET type enum case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 8)
FR17-TC-009 | Security | GET sensitive data | GET coupon list | Không trả password, JWT, reset token hoặc full user record | VALID | Reviewed against test-plans/FR17.md. The GET sensitive data case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-GET.html. | PASS |  | hw06-api-tests/reports/newman/FR17-GET.html (Iteration 9)
FR17-TC-010 | State Transition; Equivalence Partitioning | GET empty state | Fixture coupons rỗng rồi GET | 2xx; body là empty array | VALID | Reviewed against test-plans/FR17.md. The GET empty state case is in scope and its expected result is testable against the reviewed requirement/specification. | Prepared fixture run passed all Newman assertions for FR17-TC-010. | PASS |  | hw06-api-tests/reports/newman/prepared/FR17-TC-010.html; hw06-api-tests/reports/newman/prepared/FR17-TC-010.json
FR17-TC-011 | Positive | Positive create percent | POST body C0 bằng admin | 2xx; GET list có đúng một coupon với code mới và field khớp | VALID | Reviewed against test-plans/FR17.md. The Positive create percent case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 1)
FR17-TC-012 | Equivalence Partitioning; Positive | Positive create fixed | Đổi type fixed, discount 50000 | 2xx; GET list giữ đúng type/value | VALID | Reviewed against test-plans/FR17.md. The Positive create fixed case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 2)
FR17-TC-013 | Security; Equivalence Partitioning | Create auth missing | POST C0 không token | 4xx; GET không thấy code mới | VALID | Reviewed against test-plans/FR17.md. The Create auth missing case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 3)
FR17-TC-014 | Security | Create user role | POST C0 bằng user token | 4xx; GET không thấy code mới | VALID | Reviewed against test-plans/FR17.md. The Create user role case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 4)
FR17-TC-015 | Security; Equivalence Partitioning | Create malformed JWT | POST C0 bằng malformed token | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Create malformed JWT case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 5)
FR17-TC-016 | Security | Create forged admin JWT | POST C0 bằng forged token | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Create forged admin JWT case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 6)
FR17-TC-017 | Equivalence Partitioning | Code missing | Bỏ code | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Code missing case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 7)
FR17-TC-018 | Equivalence Partitioning | Code null | code=null | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Code null case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 8)
FR17-TC-019 | Equivalence Partitioning | Code empty | code="" | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Code empty case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 9)
FR17-TC-020 | Data Integrity | Code duplicate | Dùng code SAVE10 đã tồn tại | 4xx; chỉ một SAVE10 tồn tại; không lộ raw SQLite error | VALID | Reviewed against test-plans/FR17.md. The Code duplicate case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 5 to deeply equal 4 | FAIL | #5 | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 10); https://github.com/venncoder08/HW06_API_Testing/issues/5
FR17-TC-021 | Equivalence Partitioning | Code number type | code=123 | 4xx; không coercion thành code string | VALID | Reviewed against test-plans/FR17.md. The Code number type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 11)
FR17-TC-022 | Equivalence Partitioning | Code boolean type | code=true | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Code boolean type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 12)
FR17-TC-023 | Equivalence Partitioning | Code object type | code={} | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Code object type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 13)
FR17-TC-024 | Equivalence Partitioning | Code array type | code=[] | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Code array type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 14)
FR17-TC-025 | Security | Code SQL injection | code="X'); DROP TABLE coupons; --" | Không thực thi SQL; seed coupons và table vẫn tồn tại; không lộ SQL/stack trace | VALID | Reviewed against test-plans/FR17.md. The Code SQL injection case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 15)
FR17-TC-026 | Security | Code XSS API portion | code="<script>alert(1)</script>" | Không server-side execution/5xx; response là JSON; nếu lưu thì GET trả literal string | VALID | Reviewed against test-plans/FR17.md. The Code XSS API portion case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 16)
FR17-TC-027 | Equivalence Partitioning | Type missing | Bỏ type | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Type missing case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 17)
FR17-TC-028 | Equivalence Partitioning | Type null | type=null | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Type null case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 18)
FR17-TC-029 | Equivalence Partitioning | Type empty | type="" | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Type empty case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 19)
FR17-TC-030 | Equivalence Partitioning; Positive | Type percent | type="percent" | 2xx; GET trả percent | VALID | Reviewed against test-plans/FR17.md. The Type percent case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 20)
FR17-TC-031 | Equivalence Partitioning; Positive | Type fixed | type="fixed" | 2xx; GET trả fixed | VALID | Reviewed against test-plans/FR17.md. The Type fixed case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 21)
FR17-TC-032 | Equivalence Partitioning | Type invalid enum | type="percentage" | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Type invalid enum case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 22)
FR17-TC-033 | Equivalence Partitioning | Type number | type=1 | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Type number case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: type: expected '1' to deeply equal 1 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 23)
FR17-TC-034 | Equivalence Partitioning | Type object | type={} | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Type object case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: type: expected '[object Object]' to deeply equal {} | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 24)
FR17-TC-035 | Equivalence Partitioning | Type array | type=[] | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Type array case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: type: expected '[object Object]' to deeply equal [] | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 25)
FR17-TC-036 | Equivalence Partitioning | Discount missing | Bỏ discount_value | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Discount missing case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 26)
FR17-TC-037 | Equivalence Partitioning | Discount null | discount_value=null | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Discount null case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 27)
FR17-TC-038 | Boundary; Positive | Discount lower valid | discount_value=1 | 2xx; GET giữ giá trị 1 | VALID | Reviewed against test-plans/FR17.md. The Discount lower valid case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 28)
FR17-TC-039 | Equivalence Partitioning | Discount zero | discount_value=0 | 4xx; phải dương | VALID | Reviewed against test-plans/FR17.md. The Discount zero case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 29)
FR17-TC-040 | Equivalence Partitioning | Discount negative | discount_value=-1 | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Discount negative case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 30)
FR17-TC-041 | Functional | Discount positive decimal | discount_value=10.5 | 2xx; requirement chỉ yêu cầu dương; GET không được âm thầm đổi giá trị | VALID | Reviewed against test-plans/FR17.md. The Discount positive decimal case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 31)
FR17-TC-042 | Equivalence Partitioning | Discount numeric string | discount_value="10" | 4xx; request contract dùng number | VALID | Reviewed against test-plans/FR17.md. The Discount numeric string case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: discount_value: expected 10 to deeply equal '10' | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 32)
FR17-TC-043 | Equivalence Partitioning | Discount boolean | discount_value=true | 4xx; không coercion | VALID | Reviewed against test-plans/FR17.md. The Discount boolean case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: discount_value: expected 1 to deeply equal true | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 33)
FR17-TC-044 | Equivalence Partitioning | Discount object | discount_value={} | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Discount object case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: discount_value: expected '[object Object]' to deeply equal {} | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 34)
FR17-TC-045 | Equivalence Partitioning | Discount array | discount_value=[] | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Discount array case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: discount_value: expected '[object Object]' to deeply equal [] | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 35)
FR17-TC-046 | Equivalence Partitioning | Min amount missing | Bỏ min_order_amount | 4xx; field bắt buộc | VALID | Reviewed against test-plans/FR17.md. The Min amount missing case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 36)
FR17-TC-047 | Equivalence Partitioning | Min amount null | min_order_amount=null | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Min amount null case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 37)
FR17-TC-048 | Boundary | Min lower boundary | min_order_amount=0 | 2xx; GET giữ giá trị 0 | VALID | Reviewed against test-plans/FR17.md. The Min lower boundary case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 38)
FR17-TC-049 | Positive | Min positive | min_order_amount=1 | 2xx; GET giữ giá trị 1 | VALID | Reviewed against test-plans/FR17.md. The Min positive case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 39)
FR17-TC-050 | Equivalence Partitioning | Min negative | min_order_amount=-1 | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Min negative case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 40)
FR17-TC-051 | Positive | Min positive decimal | min_order_amount=0.5 | 2xx; requirement chỉ quy định >=0; GET không đổi giá trị | VALID | Reviewed against test-plans/FR17.md. The Min positive decimal case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 41)
FR17-TC-052 | Equivalence Partitioning | Min numeric string | min_order_amount="200000" | 4xx; không coercion | VALID | Reviewed against test-plans/FR17.md. The Min numeric string case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: min_order_amount: expected 200000 to deeply equal '200000' | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 42)
FR17-TC-053 | Equivalence Partitioning | Min boolean | min_order_amount=false | 4xx; không coercion thành 0 | VALID | Reviewed against test-plans/FR17.md. The Min boolean case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: min_order_amount: expected +0 to deeply equal false | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 43)
FR17-TC-054 | Equivalence Partitioning | Min object | min_order_amount={} | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Min object case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: min_order_amount: expected '[object Object]' to deeply equal {} | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 44)
FR17-TC-055 | Equivalence Partitioning | Min array | min_order_amount=[] | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Min array case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: min_order_amount: expected '[object Object]' to deeply equal [] | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 45)
FR17-TC-056 | Equivalence Partitioning | Expiry missing | Bỏ expired_at | 4xx; field bắt buộc | VALID | Reviewed against test-plans/FR17.md. The Expiry missing case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 46)
FR17-TC-057 | Equivalence Partitioning | Expiry null | expired_at=null | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Expiry null case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 47)
FR17-TC-058 | Equivalence Partitioning | Expiry empty | expired_at="" | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Expiry empty case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 48)
FR17-TC-059 | Equivalence Partitioning; Positive | Expiry valid future | expired_at="2099-12-31" | 2xx; GET trả ngày parseable tương ứng | VALID | Reviewed against test-plans/FR17.md. The Expiry valid future case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 49)
FR17-TC-060 | Equivalence Partitioning; Positive | Expiry valid leap day | expired_at="2032-02-29" | 2xx; GET trả ngày hợp lệ | VALID | Reviewed against test-plans/FR17.md. The Expiry valid leap day case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 50)
FR17-TC-061 | Equivalence Partitioning; Positive | Expiry valid past | expired_at="2020-01-01" | 2xx; FR17 chỉ yêu cầu field ngày; FR09 chịu trách nhiệm từ chối coupon hết hạn | VALID | Reviewed against test-plans/FR17.md. The Expiry valid past case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 51)
FR17-TC-062 | Equivalence Partitioning | Expiry invalid date | expired_at="2031-02-29" | 4xx; không tạo coupon với ngày không tồn tại | VALID | Reviewed against test-plans/FR17.md. The Expiry invalid date case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 52)
FR17-TC-063 | Equivalence Partitioning | Expiry invalid format | expired_at="not-a-date" | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Expiry invalid format case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 53)
FR17-TC-064 | Equivalence Partitioning | Expiry number type | expired_at=20991231 | 4xx; request contract dùng date string | VALID | Reviewed against test-plans/FR17.md. The Expiry number type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 54)
FR17-TC-065 | Equivalence Partitioning | Expiry object type | expired_at={} | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Expiry object type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: expired_at: expected '[object Object]' to deeply equal {} | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 55)
FR17-TC-066 | Equivalence Partitioning | Max uses missing | Bỏ max_uses_per_user | 4xx; field bắt buộc | VALID | Reviewed against test-plans/FR17.md. The Max uses missing case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 56)
FR17-TC-067 | Equivalence Partitioning | Max uses null | max_uses_per_user=null | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Max uses null case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: max_uses_per_user: expected 1 to deeply equal null | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 57)
FR17-TC-068 | Boundary; Positive | Max uses lower valid | max_uses_per_user=1 | 2xx; GET giữ giá trị 1 | VALID | Reviewed against test-plans/FR17.md. The Max uses lower valid case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 58)
FR17-TC-069 | Positive | Max uses positive | max_uses_per_user=2 | 2xx; GET giữ giá trị 2 | VALID | Reviewed against test-plans/FR17.md. The Max uses positive case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 59)
FR17-TC-070 | Equivalence Partitioning | Max uses zero | max_uses_per_user=0 | 4xx; phải >=1 | VALID | Reviewed against test-plans/FR17.md. The Max uses zero case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: max_uses_per_user: expected 1 to deeply equal +0 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 60)
FR17-TC-071 | Equivalence Partitioning | Max uses negative | max_uses_per_user=-1 | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Max uses negative case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 61)
FR17-TC-072 | Equivalence Partitioning | Max uses numeric string | max_uses_per_user="1" | 4xx; không coercion | VALID | Reviewed against test-plans/FR17.md. The Max uses numeric string case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: max_uses_per_user: expected 1 to deeply equal '1' | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 62)
FR17-TC-073 | Equivalence Partitioning | Max uses object | max_uses_per_user={} | 4xx; server không crash | VALID | Reviewed against test-plans/FR17.md. The Max uses object case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Created field: max_uses_per_user: expected '[object Object]' to deeply equal {} | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 63)
FR17-TC-074 | Security | ID mass assignment | Gửi C0 cộng id=1 | Seed coupon ID 1 không bị overwrite; created resource không chiếm ID client chỉ định | VALID | Reviewed against test-plans/FR17.md. The ID mass assignment case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 64)
FR17-TC-075 | Concurrency; Data Integrity | Concurrent uniqueness | Gửi đồng thời hai POST admin cùng code unique | Chỉ một resource có code đó được tạo; request còn lại bị từ chối 4xx | VALID | Reviewed against test-plans/FR17.md. The Concurrent uniqueness case is in scope and its expected result is testable against the reviewed requirement/specification. | Two concurrent create requests returned HTTP 200 and 500; database rows with code HW06_FR17_075=1. Expected one 2xx, one 4xx, and one row. | FAIL | #5 | hw06-api-tests/reports/newman/prepared/PREPARED-CASES-SUMMARY.md; hw06-api-tests/reports/newman/prepared/PREPARED-RESULTS.json; https://github.com/venncoder08/HW06_API_Testing/issues/5
FR17-TC-076 | Positive | Positive delete | DELETE ID vừa tạo bằng admin token | 2xx; GET list không còn ID/code đó | VALID | Reviewed against test-plans/FR17.md. The Positive delete case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 1)
FR17-TC-077 | Security; Equivalence Partitioning | Delete auth missing | DELETE ID tồn tại không token | 4xx; coupon vẫn tồn tại | VALID | Reviewed against test-plans/FR17.md. The Delete auth missing case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 2)
FR17-TC-078 | Security | Delete user role | DELETE ID tồn tại bằng user token | 4xx; coupon vẫn tồn tại | VALID | Reviewed against test-plans/FR17.md. The Delete user role case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 2 to deeply equal 4 ¦ Delete state is correct: expected false to deeply equal true | FAIL | #6 | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 3); https://github.com/venncoder08/HW06_API_Testing/issues/6
FR17-TC-079 | Security; Equivalence Partitioning | Delete malformed JWT | DELETE ID tồn tại bằng malformed token | 4xx; coupon vẫn tồn tại | VALID | Reviewed against test-plans/FR17.md. The Delete malformed JWT case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 4)
FR17-TC-080 | Equivalence Partitioning | Delete nonexistent | DELETE ID 999999 | Không coupon nào bị xóa; response không lộ SQL/stack trace; exact status là specification gap | VALID | Reviewed against test-plans/FR17.md. The Delete nonexistent case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 5)
FR17-TC-081 | Equivalence Partitioning | Delete ID zero | DELETE ID 0 | Không coupon nào bị xóa; server tiếp tục hoạt động | VALID | Reviewed against test-plans/FR17.md. The Delete ID zero case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 6)
FR17-TC-082 | Equivalence Partitioning | Delete ID negative | DELETE ID -1 | Không coupon nào bị xóa; server tiếp tục hoạt động | VALID | Reviewed against test-plans/FR17.md. The Delete ID negative case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 7)
FR17-TC-083 | Equivalence Partitioning | Delete ID string | DELETE ID abc | Không coupon nào bị xóa; response không lộ SQL/stack trace | VALID | Reviewed against test-plans/FR17.md. The Delete ID string case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 8)
FR17-TC-084 | Security | Delete SQL injection | DELETE encoded ID 1 OR 1=1 | Không mass-delete; seed coupon count không giảm ngoài target | VALID | Reviewed against test-plans/FR17.md. The Delete SQL injection case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 9)
FR17-TC-085 | State Transition | Double delete state | Delete một ID, sau đó delete lại cùng ID | Lần đầu 2xx; sau lần hai resource vẫn không tồn tại và coupon khác không đổi; status lần hai là specification gap | VALID | Reviewed against test-plans/FR17.md. The Double delete state case is in scope and its expected result is testable against the reviewed requirement/specification. | First DELETE HTTP 200; second DELETE HTTP 200 (exact second status is a specification gap); target rows=0; SAVE10 rows=1. | PASS |  | hw06-api-tests/reports/newman/prepared/PREPARED-CASES-SUMMARY.md; hw06-api-tests/reports/newman/prepared/PREPARED-RESULTS.json
FR17-TC-086 | State Transition | Create-read-delete lifecycle | Create unique coupon, GET xác nhận, DELETE, GET lại | State lần lượt absent -> present -> absent | VALID | Reviewed against test-plans/FR17.md. The Create-read-delete lifecycle case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 11)
FR17-TC-087 | Data Integrity | Delete isolation | Delete coupon A khi coupon B tồn tại | Chỉ A biến mất; B và seed coupons giữ nguyên | VALID | Reviewed against test-plans/FR17.md. The Delete isolation case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-DELETE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-DELETE.html (Iteration 12)
FR17-TC-088 | Equivalence Partitioning | Malformed JSON | POST body JSON thiếu dấu đóng | 4xx; không tạo coupon; server vẫn phục vụ GET | VALID | Reviewed against test-plans/FR17.md. The Malformed JSON case is in scope and its expected result is testable against the reviewed requirement/specification. | All Newman assertions passed in FR17-CREATE.html. | PASS |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 66)
FR17-TC-089 | Equivalence Partitioning | Wrong content type | POST C0 với Content-Type không phải JSON | 4xx; không tạo coupon | VALID | Reviewed against test-plans/FR17.md. The Wrong content type case is in scope and its expected result is testable against the reviewed requirement/specification. | Newman assertions failed: Expected HTTP status class: expected 5 to deeply equal 4 | FAIL |  | hw06-api-tests/reports/newman/FR17-CREATE.html (Iteration 67)

## Summary
Metric | Value | Details
Feature | FR17
Total Test Cases | 89
Audit VALID | 89 | Design reviewed independently from execution result
Audit INVALID | 0
Audit INCOMPLETE | 0
Execution PASS | 40 | All Newman assertions passed
Execution FAIL | 49 | At least one Newman assertion failed
Execution BLOCKED | 0 | Fixture/manual/stateful execution was not conclusive
Linked GitHub Bugs | 3 | #4, #5, #6
Bug ID | GitHub Issue | Mapped Test Cases
#4 | https://github.com/venncoder08/HW06_API_Testing/issues/4 | FR17-TC-003
#5 | https://github.com/venncoder08/HW06_API_Testing/issues/5 | FR17-TC-020, FR17-TC-075
#6 | https://github.com/venncoder08/HW06_API_Testing/issues/6 | FR17-TC-078